Outer Banks Repeater Association

OBRA Operation Ocean Mist COMMEX Exercise Plan and IAP Rev 3.0

Upgraded Functional EMCOMM/AUXCOMM Exercise Package

Exercise: Operation Ocean Mist 26 | Operational Period: June 2026, 0930-1330 EDT

All exercise traffic shall be prefixed and closed with: THIS IS AN EXERCISE.

# 1. Exercise Purpose

Operation Ocean Mist 26 is a functional communications exercise designed to test OBRA operating procedures for activating, controlling, staffing, and sustaining multiple directed amateur radio voice nets during a fast-moving hazardous materials incident affecting Dare County and the Outer Banks.

The exercise stresses voice net discipline, Net Control rotation, PACE failover, Winlink/ICS-213 message handling, commercial communications degradation, and failure of selected OBRA/repeater/internet-linked systems. Dare County Emergency Management and public safety agencies are represented by exercise controllers unless separately participating.

# 2. Exercise Identification

| Item | Value |
| --- | --- |
| Exercise Name | Operation Ocean Mist 26 |
| Exercise Type | Functional communications exercise (COMMEX) |
| Operational Period | 0930-1330 EDT / 1330-1730 UTC |
| Scenario | Toxic industrial chemical release from tanker crash on NC-158 with plume movement and communications degradation |
| Exercise Coordinator | Dare County AUXCOMM Coordinator - Malcolm Green, KY4RY |
| Primary Participating Organization | Outer Banks Repeater Association (OBRA) |
| Supporting Capabilities | AUXCOMM, directed voice nets, DMR where available, Winlink, WebEOC logging, simplex fallback, HF backup |
| Exercise Control | Controller/Evaluator cell; all traffic prefixed with THIS IS AN EXERCISE |

# 3. Scenario Narrative

At approximately 0810 local time, a commercial tanker carrying industrial chemicals jackknifes on NC-158 near the northern edge of the fictional community of Ocean View. The tanker sustains catastrophic damage and releases a toxic gas cloud drifting south toward populated areas. The incident causes public concern, congested 911 access, degraded cellular service, intermittent internet service, and pressure on public safety communications.

Dare County activates the EOC and requests AUXCOMM/OBRA support for backup communications, field situation reporting, shelter communications, and formal message traffic. OBRA initiates its callout process and establishes directed emergency nets.

# 4. Exercise Scope and Assumptions

- No real hazardous materials are involved; all locations and incident effects are simulated unless specifically authorized by Exercise Control.

- Exercise players may operate from home stations, mobile stations, EOC/shelter positions, or designated radio rooms.

- All traffic uses exercise language and does not imply a real emergency.

- Net Control Stations may be intentionally overloaded to test relief, logging, and traffic prioritization.

- Repeater, DMR, Winlink, cellular, internet, and commercial power failures may be simulated by controller inject even if systems remain technically functional.

# 5. Exercise Objectives

- Activate OBRA callout and establish an initial directed Command Net within 20 minutes of notification.

- Establish and operate at least three directed voice nets: Command, Tactical, and Shelter/Welfare/Logistics.

- Demonstrate disciplined NCS procedures, including check-ins, tactical call signs, priority traffic, read-backs, net pauses, and NCS relief.

- Validate OBRA PACE plan under simulated repeater failure, internet-linked DMR failure, Winlink congestion, cellular degradation, and commercial power/site impacts.

- Pass and track ICS-213 messages by Winlink when available and by voice relay when digital paths fail.

- Produce usable ICS documentation: IAP, ICS-205, ICS-213, ICS-214, ICS-309, roster, and hot wash/AAR input.

# 6. Net Architecture

| Net | Purpose | Primary Users | Initial Channel | Trigger to Activate |
| --- | --- | --- | --- | --- |
| Command Net | EOC, ICP, AUXCOMM Lead, NCS coordination | EOC, ICP, COML/AUXCOMM, primary NCS | KDH W4PCN 145.110 PL 131.8 | Exercise start / OBRA activation |
| Tactical Net | Field operators, mobile units, site reports | Mobile Alpha/Bravo/Charlie, field teams | TAC-1 or assigned repeater | Field reports exceed Command Net capacity |
| Shelter/Welfare Net | Shelter status, logistics, welfare traffic | Shelter operator, Logistics NCS, welfare stations | DMR local TG or TAC-2 | Shelter opening inject |
| Winlink/Digital Support | ICS-213 and formal written traffic | EOC Winlink, RMS support, message unit | Skyco RMS 145.610 / HF backup | Formal message requested |
| HF/Regional Backup | Regional contact if local systems degraded | HF operators, EOC liaison | 7.242 MHz LSB or assigned | VHF repeater/simplex failure or EOC request |

# 7. PACE Communications Plan

| PACE Level | Method | Primary Use | Failure Condition / Action |
| --- | --- | --- | --- |
| Primary | KDH W4PCN 145.110 MHz PL 131.8 FM Analog | Command Net and initial directed emergency net | If intermittent or unavailable, move Command Net to Alternate. |
| Alternate | Mamie/NCPRN/available OBRA repeater or DMR local path | Command or logistics overflow if RF path is available | If internet-linked path fails, do not rely on hotspot/BrandMeister for critical traffic. |
| Contingency | FM simplex TAC-1 146.550, TAC-2 146.580, TAC-3 147.555 | Field tactical, shelter, and relay operations | Use relay stations and geographic net split if simplex coverage is limited. |
| Emergency | HF voice, HF Winlink, Skyco RMS/alternate RMS, runner/telephone when available | Out-of-area contact, formal backup message traffic | Use only when local VHF/UHF paths are unavailable or EOC directs. |

# 8. Master Timeline and Timed Inject Matrix

| Time | Inject | Expected Actions | Evaluator Focus |
| --- | --- | --- | --- |
| 0930 | Exercise start. Dare County EOC requests OBRA activation for toxic release COMMEX. | Initiate OBRA callout; open Command Net; announce directed net rules. | Activation discipline; proper EXERCISE prefix. |
| 0945 | 911 overload and public panic reports; EOC requests radio backup status. | NCS establishes check-in order; EOC radio desk begins ICS-214 and ICS-309. | Net control opening, check-in, logging. |
| 1000 | Field report: respiratory distress near Ocean View Elementary School. | Generate ICS-213 priority message to EOC; relay by voice and Winlink if available. | Message precedence and read-back accuracy. |
| 1015 | Wind shift moves plume toward Nags Head. | Command Net broadcasts situation update; Tactical Net collects field reports. | Directed net traffic control and common operating picture. |
| 1030 | Ocean View High School shelter opens and requests comms support. | Activate Shelter/Welfare Net; assign shelter operator and reporting interval. | Multiple directed net activation. |
| 1045 | Commercial cellular data degrades; SMS unreliable. | Shift all critical coordination to amateur nets; test PACE status. | PACE transition and operator awareness. |
| 1100 | BrandMeister internet path fails; hotspot users lose access. | Move DMR/logistics traffic to available repeater path or analog alternate. | Understanding RF repeater vs internet-linked DMR dependency. |
| 1115 | KDH primary repeater intermittent due site power issue. | NCS announces alternate plan; test Mamie/NCPRN or simplex contingency. | Controlled failover without losing net discipline. |
| 1130 | Primary repeater unavailable for 20 minutes. | Split Command/Tactical by PACE: Command on alternate, field ops on TAC-1 simplex. | Net split, relays, station assignments. |
| 1145 | EOC requests resource request for shelter generator fuel. | Use ICS-213; assign priority; route to Logistics; confirm receipt. | Formal message handling. |
| 1200 | Skyco Winlink RMS congested/unavailable. | Use voice ICS-213 relay with read-back; log manual handling. | Digital-to-voice fallback. |
| 1215 | Rumor control: social media reports evacuation order not issued by IC. | NCS blocks rumor traffic; relay only approved IC/EOC information. | Information discipline. |
| 1230 | NCS fatigue: high traffic volume and doubled check-ins. | Rotate NCS and shadow; enforce tactical call signs and priority traffic only. | NCS relief and net load management. |
| 1245 | Shelter requests medical transport for vulnerable resident. | Life-safety priority message; confirm EOC/EMS notification. | Priority handling and closed-loop communications. |
| 1300 | All repeaters restored except simulated BrandMeister link; EOC requests status roll-up. | Collect SITREP from each net; compile ICS-214/309 summary. | Situation reporting and documentation. |
| 1315 | Begin demobilization. | Close lower-priority nets; retain Command Net until Controller release. | Orderly demob and logs. |
| 1330 | End exercise. | Terminate exercise traffic; start hot wash. | AAR capture and improvement items. |

# 9. Staffing and Assignments

| Position/Team | Primary Assignment | Suggested Staffing | Reporting To |
| --- | --- | --- | --- |
| Exercise Director | Overall conduct, start/stop, safety override | Malcolm Green KY4RY or designee | Exercise Control |
| Lead Controller | Inject delivery, controller synchronization | Assigned controller | Exercise Director |
| AUXCOMM Lead / COML Role | Communications plan, net structure, resource coordination | KY4RY or assigned COML/AUXCOMM lead | EOC/Exercise Director |
| Command Net NCS | Open and control Command Net, maintain ICS-309 | 1 NCS + 1 shadow per 30 minutes | AUXCOMM Lead |
| Tactical Net NCS | Control field traffic and tactical reports | 1 NCS + 1 relief | Command Net NCS |
| Shelter/Welfare NCS | Control shelter and logistics traffic | 1 NCS + 1 relief | Command Net NCS |
| Winlink Operator | Send/receive ICS-213 and maintain message tracker | 1-2 operators | EOC Radio Desk |
| EOC Radio Desk | Voice coordination, WebEOC support, logs | 2-3 operators | AUXCOMM Lead |
| Field/Mobile Operators | Situation reports, relay, shelter status | As assigned | Tactical or Shelter NCS |

# 10. Directed Net Operating Procedures to be Tested

- Open each net with a formal net script: identify NCS, purpose, frequency/channel, directed net status, exercise language, and check-in instructions.

- Use tactical call signs for assigned incident functions while retaining FCC identification requirements.

- Pause the net regularly for priority or emergency exercise traffic.

- Require read-back for life-safety, resource request, evacuation/shelter, and formal ICS-213 traffic.

- Maintain an ICS-309 or equivalent net log for each net.

- Rotate NCS at planned intervals or on controller inject when fatigue/overload occurs.

- When failover occurs, announce the move three times if possible, identify the new channel, and log the time and reason.

# 11. Success Criteria

| Capability | Target Standard |
| --- | --- |
| Activation | Callout initiated and Command Net open within 20 minutes. |
| Multiple nets | At least three directed nets established and controlled without unmanaged doubling or loss of priorities. |
| PACE failover | Players transition from primary repeater to alternate/simplex/digital/voice fallback within 10 minutes of inject. |
| Formal messages | At least three ICS-213 messages generated, routed, acknowledged, and logged. |
| Documentation | ICS-205, ICS-214, ICS-309, message tracker, and hot wash notes completed sufficiently for AAR. |
| Safety and realism | No public alarm; all exercise traffic clearly identified. |

# 12. Safety, Control, and Termination

- Any participant may stop exercise play for a real-world safety issue using the phrase REAL WORLD SAFETY.

- Controllers may pause, repeat, or skip injects if safety, weather, or operational conditions require.

- No participant shall self-deploy to a hazardous area or interfere with public safety operations.

- Mobile operators shall comply with all traffic laws and may pull over before transmitting or logging.

# 13. Hot Wash Focus Questions

- Did OBRA callout work quickly enough and reach the right operators?

- Were directed net scripts and NCS procedures clear and disciplined?

- Could operators distinguish Command, Tactical, Shelter/Welfare, and Logistics traffic?

- Did PACE transitions work in practice or only on paper?

- Were ICS-213, ICS-214, and ICS-309 records complete enough to reconstruct the exercise?

- What changes are required to OBRA SOPs, codeplugs, training, or repeater status procedures?